## Progress & quality
See Documentation roadmap objectives for an explanation of objectives ☞ | Roadmap owner | 2 of 37 OK for roadmap sprint | Agreement | Last review | QI 23.07 | QI now | Objectives 23.10 | Progress | Completeness % | Diátaxis | Docs homepage | Tutorial | Marketing content alignment | Inclusive language | Styleguide | Automated spelling checks | Content automation | Automated quality controls | Project governance | Feedback mechanism | Community engagement | Security topic | Performance topic | Energy efficiency topic | IAM topic | Ubuntu Pro reference (where appropriate)
|  |  | Progress | [6 empty] | Fundamentals |  |  |  | Checks |  |  |  |  | The public |  |  | Topics
[6 empty] | 204 |  |  |  | 5 | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 5 | 1 | 1 | 1 | 1 | 1
Examples
Turtle Graphics | Anon Fakey | TRUE | Agreed | 2023-06-30 | 115 | 140 |  | 25 | 68.6275 | Mature | Done | First results | Started | Started | First results | Blocked | Started | First results | Done | Done | Started | Started | Planned | First results | First results | Done
Rubik's Cube | Unreal Someone | TRUE | Agreed | 2023-09-04 | 118 | 118 |  | 0 | 57.8431 | Mature | Done | Mature | Started | Started | First results | Blocked |  |  | Done | Done | Started | Started | Planned | No activity
Arm Wrestling | Dr Eng. Manager | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0
|  | FALSE |  |  |  | 0 |  | 0 | 0

## Data (hidden)
Next roadmap review | 2023-10-30
Last roadmap review | 2023-07-24

## Lookups (hidden)
No activity | 0
Deferred | 0
n/a | 0
Blocked | 0
Planned | 1
Agreed | 2
Started | 3
First results | 4
Mature | 6
Done | 6